## BACK_LOG
Site Area | Issue | Description | Priority | Completed? | Release Completed In
Part List | Make the tooltip link to collectibles | The tooltip in the part's list needs to be more sticky and allow us to link to the collectible it belongs to
Part List | Indicate if the collectible linked to is pending or active | In the tooltip in the part's list we need to indicate if that is an active link or a pending link
Collectible's Uploads | Allow the deletion of the primary photo | Update so that we can delete the primary photo we also need to make sure we can assign a different photo as the primary photo
User Uploads | Update User uploads to use the new process | Use the same process for user uploads that we are using for collectibles uploads |  | Yes | 1.6
User Profile | Put back Edit History | Going to need a new way to look at the user's edit history
Parts | Allow adding uploads per part | We need to be able to edit a part to upload a photo, I think this will involve having a better part view page that we can make put that logic there.
Edit Collectible | Be able to search a list of parts when adding existing part to a collectible | We need to support both adding existing parts by collectible and by the part list
Collectible | Put Features back in | We need to put features back in, they should be similar to a part but there is no linking and they get a subset they can select from. The edit process should just put a list of the selected features in a single column so we can use that to know what changed...make it easy
Admin | Add and Update Attribute Category
Part Edit/ Collectible Edit | Loading animations when doing ajax calls |  | 1
Edit Collectible | When adding existing part, indicate how many that collectible has | In the collectibles parts list, show how many that current collectible has
Edit Collectible | When adding existing part, only show name or description | In the collectibles parts list, only show name or description
Edit Collectible | When adding existing part, be able to add more than one at a time | When adding an existing attribute we need to enhance it so that you can select a collectible and then select all of the attributes you want to add from that collectible - go WAY faster
Edit Collectible | Remove Part -link | Support admin path
Collectible Detail - Part List | Update to show other collectibles the part is linked to | Update the part list to show other collectibles the part is linked too