## BACK_LOG
Site Area | Issue | Description | Priority | Completed? | Release Completed In
Part List | Make the tooltip link to collectibles | The tooltip in the part's list needs to be more sticky and allow us to link to the collectible it belongs to
Part List | Indicate if the collectible linked to is pending or active | In the tooltip in the part's list we need to indicate if that is an active link or a pending link
Collectible's Uploads | Allow the deletion of the primary photo | Update so that we can delete the primary photo we also need to make sure we can assign a different photo as the primary photo
User Uploads | Update User uploads to use the new process | Use the same process for user uploads that we are using for collectibles uploads |  | Yes | 1.6
User Profile | Put back Edit History | Going to need a new way to look at the user's edit history
Parts | Allow adding uploads per part | We need to be able to edit a part to upload a photo, I think this will involve having a better part view page that we can make put that logic there.
Edit Collectible | Be able to search a list of parts when adding existing part to a collectible | We need to support both adding existing parts by collectible and by the part list
Collectible | Put Features back in | We need to put features back in, they should be similar to a part but there is no linking and they get a subset they can select from. The edit process should just put a list of the selected features in a single column so we can use that to know what changed...make it easy
Admin | Add and Update Attribute Category
Part Edit/ Collectible Edit | Loading animations when doing ajax calls |  | 1
Edit Collectible | When adding existing part, indicate how many that collectible has | In the collectibles parts list, show how many that current collectible has
Edit Collectible | When adding existing part, only show name or description | In the collectibles parts list, only show name or description
Edit Collectible | When adding existing part, be able to add more than one at a time | When adding an existing attribute we need to enhance it so that you can select a collectible and then select all of the attributes you want to add from that collectible - go WAY faster
Edit Collectible | Remove Part -link | Support admin path
Collectible Detail - Part List | Update to show other collectibles the part is linked to | Update the part list to show other collectibles the part is linked too
Collectible History | Put back Edit History | Need a better system to show changes over time. I think we will use a collectible_activity table to store all activity for a collectible. This would only show the approved stuff. We would need to store the edit_id and then version_id of the corresponding table
Convert Edits to Text | Need a way to convert the edit tables into a textual format | This task would convert any current edit row into a textual format. If I update the cost of a collectible = "Cost was update" or "New Attribute added to Collectible" or "Photo removed from Collectible". This would be used in the collectible history view as well as the activity view for when viewing edits